## Sheet1
Bug ID | Related TC | Title | Severity | Priority | Status | Steps to Reproduce | Attachments
BUG_001 | 7 | Inconsistent height of college boxes | Low | Medium | Open | 1. Open Colleges page2. Scroll to Science Colleges3. Observe the height of subject boxes | https://i.imgur.com/5wYgilG.png
BUG_002 | 8 | Missing registration success message | Medium | High | Open | 1. Open registration page2. Enter valid registration data3. Submit form and check for success message | https://i.imgur.com/ns8I6c3.png
BUG_003 | 9 | Missing City selection for Jordan universities | Low | Medium | Open | 1. Open registration form2. Select Country = Jordan3. Verify City selection field is available | https://i.imgur.com/jLtMaFd.png
BUG_004 | 10 | Number field accepts letters | Medium | High | Open | 1. Open registration form2. Enter letters in number field3. Check validation | https://i.imgur.com/jLtMaFd.png
BUG_005 | 11 | No password strength validation | Medium | Medium | Open | 1. Open registration page2. Enter a weak password3. Submit form and observe any warnings | https://i.imgur.com/RSXvq8L.png
BUG_006 | 12 | Invalid email allowed during registration | High | High | Open | 1. Register with invalid email format2. Attempt to login with same email3. Observe login failure | https://i.imgur.com/NdBRrgN.png